MONTANA CDBG PROGRAM and NSP

October 2013 GRANT ADMINISTRATION MANUAL

## TABLE OF CONTENTS

CHAPTER I -- PROJECT START-UP

### I. 	OVERVIEW …………………………………………………………………………………………	1-2

II. 	APPLICABLE REQUIREMENTS.………………………………………………………………...	1-3

A.	FEDERAL.…………………………………………………………………. .…………………..	1-3

B. 	STATE	.…………………………………………………………………. .………………………	1-4

III. 	STEPS FOR PROJECT START-UP.…………………………………………………………….	1-5

A.	GRANT AWARD LETTER.……………………………………………………………………..	1-5

B.	PREPARING THE CONTRACT.………………………………………………………………	1-5

C.	AMENDING THE CONTRACT.………………………………………………………………..	1-7

D.	INCURRING START-UP COSTS.…………………………………………………………….	1-7

1.	Environmental Exemption for Administrative Activities.………………………………...	1-8

2.  	Reimbursement of Activities...…………………………………………………………….	1-8

E. 	ATTENDING CDBG GRANT ADMINISTRATION WORKSHOP.………………………….	1-9

F. 	ESTABLISHING A MANAGEMENT PLAN FOR PROJECT ADMINISTRATION.……….	1-9

1.	Administration by Public Employees.……………………………………………………..	1-11

2.	Management by Private Contractor/Consultant.………………………………………...	1-12

G.	ESTABLISHING A PROGRAM INCOME PLAN.…………………………………………….	1-13

H.	PREPARING THE PROJECT IMPLEMENTATION SCHEDULE.…………………………	1-14

1. 	Project Start-up Requirements.……………………………………………………………	1-14

2.	Commitment of Non-CDBG Resources.………………………………………………….	1-14

3.	Timely Project Completion.………………………………………………………………...	1-15

4.	Applications on Behalf of Rural Special Improvement Districts (RSID's)……………..	1-16

I.	ADDITIONAL START-UP ACTIVITIES.………………………………………………………	1-16	J. 	COMPLETING SIGNATURE AND DEPOSITORY FORMS.……………………………….	1-17

K. 	ESTABLISHING PROJECT FILES.…………………………………………………………...	1-18

EXHIBITS.…………………….…………………………………………………………………. ………	1-23

CHAPTER 2 -- ENVIRONMENTAL REVIEW

I.	OVERVIEW.…………………………………………………………... .…………………………..	2-2

II.	APPLICABLE REQUIREMENTS.…………………………………………………………... .…..	2-7

A.	FEDERAL.…………………………………………………………... .…………………………	2-7       B.	STATE	.…………………………………………………………... .…………………………….	2-10

III.	GRANTEE RESPONSIBILITIES.…………………………………………………………... .…..	2-11

IV.	ENVIRONMENTAL FINDING A.…………………………………………………………... .……	2-15

V.	ENVIRONMENTAL FINDING B.…………………………………………………………... .……	2-17

VI.	ENVIRONMENTAL FINDING C.…………………………………………………………... .……	2-24

VII.	ENVIRONMENTAL FINDING D.…………………………………………………………... .……	2-29

VIII.	ENVIRONMENTAL FINDING E.…………………………………………………………... .……	2-35

IX. 	OTHER ENVIRONMENTAL ISSUES.…………………………………………………………...	2-36

A.	LEAD-BASED PAINT.…………………………………………………………... .……………	2-36

B. 	ASBESTOS.…………………………………………………………... .……………………….	2-37

C.	RADON.…………………………………………………………... .……………………………	2-38

EXHIBITS.……………………………………………….………………………………………………	2-40

#### CHAPTER 3 --  PROCUREMENT STANDARDS

- I.

- OVERVIEW.……………………….………………………………………………………….......	3-2

A.	PROCUREMENT STANDARDS……………………………………………..………………..	3-2

B.	REQUIREMENTS.……………………………………………………………………………...	3-2

II. 	APPLICABLE REQUIREMENTS.……………………………………………….………………..	3-3

A.	FEDERAL.…………………………………………………………... .…………………………	3-3

B.	STATE	.…………………………………………………………... .…………………………….	3-3

III.  	GRANTEE RESPONSIBILITIES.…………………………………………………………... .…..	3-4

A.	CODE OF ETHICS.…………………………………………………………... .………………	3-4

B.	CONFLICTS OF INTEREST.…………………………………………………………... .……	3-4

C.	GENERAL PROCUREMENT POLICIES.…………………………………………………….	3-6

D.	CONTRACTING WITH DISADVANTAGED BUSINESS ENTERPRISES.……………….	3-7

E.	PROCUREMENT PROCEDURES.…………………………………………………………...	3-7

F.	SELECTING THE METHOD OF PROCUREMENT.………………………………………..	3-8

1.	Procurement of Grant Management Services.…………………………………………..	3-8

2.	Procurement of Architectural / Engineering, or Surveying Services.………………….	3-11

3.	Procurement by HUD's "Small Purchase" Procedures.………………………………...	3-11

4.	Procurement by Competitive Sealed Bid.………………………………………………..	3-13

5.	Sole Source Procurement (Noncompetitive Negotiation) .……………………………..	3-14

6.	Procurement by Competitive Proposals.…………………………………………………	3-15

G.	PREPARING A REQUEST FOR QUALIFICATIONS OR A REQUEST FOR

PROPOSALS.…………………………………………………………... .…………………..	3-16

H.	SOLICITING PROPOSALS.…………………………………………………………... .……..	3-17

I.	PRIOR COMMITMENTS TO CONSULTANTS.……………………………………………..	3-18

J.	REVIEWING PROPOSALS AND SELECTING THE CONSULTANT.……………………	3-19

K.	CHECKING REFERENCES.…………………………………………………………... .…….	3-20

L.	MDOC DEBARMENT CHECK AND REVIEW OF PROCUREMENT PROCEDURES.…	3-21

M.	CONTRACT PRICING AND METHOD OF COMPENSATION.……………………………	3-22

N.	PREPARING THE CONTRACT.…………………………………………………………... …	3-24

O.	RECORD KEEPING REQUIREMENTS.……………………………………………………..	3-25

P.	CONTRACT ADMINISTRATION AND SUPERVISION.…………………………………… 3-25

EXHIBITS.……………………..………………………………………………………….............……	3-27

### CHAPTER 4 -- FINANCIAL MANAGEMENT

I.  	OVERVIEW.………………………….…………………………………………………………......	4-2

II.  	APPLICABLE FEDERAL AND STATE REQUIREMENTS.……………………………………	4-2

A.	FEDERAL REQUIREMENTS.…………………………………………………………..……..	4-2

B.	STATE REQUIREMENTS.………………………………………………………………….....	4-3

III.	PROGRAM REQUIREMENTS.…….………………………………………………………….....	4-3

A.	PROJECT BUDGET.…………….…………………………………………………………......	4-3

B.	PROJECT ADMINISTRATION COSTS.……………………………………………………...	4-4

C.	LOCAL DEPOSITORY ACCOUNT.…………………………………………………………...	4-4

D.	PROJECT DRAWDOWNS.……….…………………………………………………………...	4-4

E.	REPORTING REQUIREMENTS..………………………………………………………….....	4-7

F. 	TWO PERCENT RETAINAGE.….………………………………………………………….....	4-7

G.	INTERIM FINANCING.…………….…………………………………………………………...	4-8

H.	PROPERTY MANAGEMENT AND DISPOSITION.…………………………………………	4-8

I.  	RETENTION – DOCUMENTS/RECORDS/REPORTS.…………………………………….	4-8

IV.	PROGRAM INCOME AND REVOLVING LOANS.……………………………………………..	4-9

V. 	GENERAL ACCOUNTING REQUIREMENTS.………………………………………………….	4-9

A.	STANDARDS FOR ACCOUNTING SYSTEMS.……………………………………………..	4-9

B.	FUND ACCOUNTING.…………………………………….…………………………………....	4-10

C.	FUND TYPE AND ACCOUNT GROUP TO BE UTILIZED.………………………………...	4-10

D.	BASIS OF ACCOUNTING.………………….………………………………………………….	4-11

E.	FUND AND ACCOUNT STRUCTURE.……………….………………………………………	4-11

F.	FIXED ASSET ACCOUNTING.…………….………………………………………………….	4-24

G.	BASIC ACCOUNTING RECORDS.……….…………………………………………………..	4-27

H.	FINANCIAL REPORTS.…………………….…………………………………………………..	4-28

VI.  	INTERNAL CONTROL.……………………….……………………………………………………	4-29

EXHIBITS.……………………………….………………………………………………….…………….	4-30

CHAPTER 5 -- CIVIL RIGHTS

I.	OVERVIEW.……………………………….………………………………………………….…….	5-2

II.    	APPLICABLE REQUIREMENTS.……………………………….………………………………..	5-5

A.	FEDERAL.……………………………….………………………………………………….……	5-5

1.	The Federal Hatch Act.……………………………….……………………………………	5-6

2.	Title VII of the Civil Rights Act of 1964.……………………………….………………….	5-5

3.  	Cranston-Gonzalez National Affordable Housing Act of 1990.………………………...	5-6

4.  	Section 504 of the Rehabilitation Act of 1973.……………………………….………….	5-6

5.  	Americans with Disabilities Act (ADA) of 1990.……………………………….…………	5-8

6.  	Architectural Barriers Act of 1968.……………………………….……………………….	5-8

7.  	Fire Administration Authorization Act of 1992.……………………………….………….	5-8

8.  	The Age Discrimination Act of 1975.……………………………….…………………….	5-8

9.  	Equal Employment Opportunities under HUD Assisted Contracts.……………………	5-9

10.	Title VIII of the Civil Rights Act of 1968, as amended by the Fair Housing

Amendments Act of 1988.……………………………….………………………………	5-9

11.	Fair Housing Act.……………………………….…………………………………………..	5-9

12.	Section 3 of the Housing and Urban Development Act of 1968.………………………	5-10

13.	Women's Business Enterprises and Minority Business Enterprises.………………….	5-11

14.	24 CFR, Part 85 - HUD Administrative Requirements for Grants (Basic Federal

Regulations - Grants and Cooperative Agreements to State, Local, and Federally

Recognized Indian Tribal Governments) .……………………………….…………….	5-12

15.	EEOC Compliance Manual, National Origin Discrimination.…………………………...	5-12

B.	STATE.……………………………….………………………………………………….……… 	5-12

III.	GRANTEE RESPONSIBILITIES.……………………………….………………………………..	5-14

1. 	PROGRAM BENEFITS.……………………………….……………………………………….	5-14

2. 	GRANTEE HIRING AND EMPLOYMENT PRACTICES.……………………………….….	5-15

3. 	CONTRACTOR AFFIRMATIVE ACTION.……………………………….…………………...	5-17

4. 	FAIR HOUSING.……………………………….………………………………………………..	5-20

5. 	ACTIONS TO AFFIRMATIVELY FURTHER FAIR HOUSING.…………………………….	5-21

6. 	HANDICAPPED ACCESSIBILITY REQUIREMENTS.……………………………….……..	5-23

1.	Accessible Communications.……………………………….……………………………..	5-25

2. 	Access to Employment.……………………………….……………………………………	5-28

3.  	Access to Program Benefits.……………………………….……………………………...	5-29

4.  	Physical Accessibility to Programs.……………………………….………………………	5-30

5.  	Data and Documentation.……………………………….…………………………………	5-32

IV.	RECORD KEEPING REQUIREMENTS.……………………………….………………………..	5-33

A. 	Local Project Civil Rights File.……………………………….………………………………...	5-33

B.	Data Collection Requirements for Ethnicity and Race.……………………………….…….	5-34

EXHIBITS.……………………………….………………………………………………….…………….	5-36

CHAPTER 6 -- LABOR STANDARDS

I.	OVERVIEW.……………………………….………………………………………………….…….	6-2

II.  	APPLICABLE REQUIREMENTS.……………………………….………………………………..	6-2

A.	FEDERAL.……………………………….………………………………………………….……	6-3

1.  	Contract Work Hours and Safety Standards Act.……………………………….……….	6-3

2.  	Copeland "Anti-Kickback" Act.……………………………….……………………………	6-4

3.  	Davis-Bacon Related Acts.……………………………….………………………………..	6-4

4.  	More Information About Davis-Bacon Act Compliance (website) .……………………	6-7

5.	Labor Standards and Projects Within Indian Reservations.……………………………	6-7

B.	STATE	.……………………………….…………………………………………………………..	6-8

1.  	Public Construction Contracts: Special Labor Conditions.……………………………..	6-8

2.	Workers' Compensation Act.……………………………….……………………………...	6-8

III. 	GRANTEE RESPONSIBILITIES.……………………………….………………………………..	6-9

Step 1 - Designate a Person to Monitor Prevailing Wage Compliance (Compliance with

federal Davis-Bacon wage provisions) .……………………………….……………………...	6-9

Step 2 - Include Labor Standards Provisions in Bid Documents.……………………………..	6-9

Step 3 - Request the Wage Rate Determination.……………………………….………………	6-10

Zone Hourly Rate Pay.……………………………….…………………………………………	6-11

Overtime Pay.……………………………….…………………………………………………...	6-12

Unclassified Workers.……………………………….………………………………………….	6-13

Step 4 - Re-verify the Wage Rate in the Solicitation for Bids.…………………………………	6-13

Step 5 - Verify Bidder Eligibility.……………………………….………………………………….	6-14

Step 6 - Inform Contractor of Federal Requirements By Conducting a Pre-construction

Conference.……………………………….………………………………………………….….	6-15

Step 7 - Monitor Contractor Performance.……………………………….………………………	6-17

Use of Volunteers.……………………………….……………………………………………...	6-18

Step 8 - Investigate Labor Standards Violations.……………………………….………………	6-19

Step 9 - Maintain Labor Standards Files.……………………………….……………………….	6-19

EXHIBITS.……………………………….………………………………………………….…………….	6-20

CHAPTER 7 -- ACQUISITION AND RELOCATION

I. 	OVERVIEW.……………………………….………………………………………………….…….	7-2

II.   	APPLICABLE REQUIREMENTS.……………………………….………………………………..	7-2

A. 	FEDERAL.……………………………….………………………………………………….……	7-2

Title IV of the Surface Transportation and Uniform Relocation Assistance Act of 1987...	7-2

Uniform Relocation Assistance and Real Property Acquisition Policies Act of 1970.……	7-2

Title VI of the Civil Rights Act of 1964.……………………………….………………………	7-3

B.	STATE	.……………………………….………………………………………………….……….	7-3

Relocation Assistance/Fair Treatment of Condemnees, Title 70, Chapter 31, Montana

Code Annotated (MCA) .……………………………….…………………………………….	7-3

III.  	GRANTEE RESPONSIBILITIES.……………………………….………………………………..	7-3

A.	VOLUNTARY ACQUISITIONS.……………………………….……………………………….	7-4

B.	NON-VOLUNTARY ACQUISITIONS.……………………………….………………………..	7-5

1. 	Obtain a Copy of HUD Handbook 1378.……………………………….………………...	7-5

2.  	Send Preliminary Acquisition Notice.……………………………….…………………….	7-5

3.  	Have Property Appraised to Determine Fair Market Value.……………………………	7-6

4.  	Have Appraisal Reviewed.……………………………….………………………………..	7-7

5.  	Determine Just Compensation for the Property.……………………………….………..	7-7

6.  	Make a Written Offer to the Owner.……………………………….………………………	7-7

7.  	Review Any Additional Materials Related to Determination of the Purchase Price.…	7-7

8.	Administrative Settlement.……………………………….………………………………...	7-7

9.	Make Payment or Make a Final Offer Before Initiating Condemnation Procedures…	7-7

C.	FINAL OFFER BEFORE INITIATING CONDEMNATION PROCEDURES -

ADMINISTRATIVE SETTLEMENT.……………………………….………………………………………………….……….	7-8

D.	CONDEMNATION PROCEEDINGS.……………………………….…………………………	7-8

E.	OTHER ACQUISITION CONSIDERATIONS.……………………………….……………….	7-9

1. 	Donations.……………………………….…………………………………………………..	7-9

2.  	Decision Not To Acquire.……………………………….………………………………….	7-9

3.  	Uneconomic Remnant.……………………………….…………………………………….	7-9

4.  	Tenant-Owned Improvements.……………………………….……………………………	7-9

5.  	Owner Retention of Improvements.……………………………….………………………	7-9

6.  	Rental Payments.……………………………….…………………………………………..	7-9

IV. 	RECORDKEEPING REQUIREMENTS.……………………………….…………………………	7-9

V.   	RELOCATION.……………………………….………………………………………………….….	7-10

EXHIBITS.……………………………….………………………………………………….…………….	7-12

CHAPTER 8 -- ECONOMIC DEVELOPMENT PROJECTS -- is available from the CDBG

Economic Development Program of the MDOC Business Resources Division:

http://businessresources.mt.gov/CDBG/default.mcpx

CHAPTER 9 -- CONSTRUCTION MANAGEMENT: PUBLIC FACILITIES AND NEW HOUSING

I. 	OVERVIEW.……………………………….………………………………………………….…….	9-2

II.    	REQUIREMENTS: SELECTING/AWARDING CONSTRUCTION CONTRACTS.………….	9-3

A. 	FEDERAL (HUD Administrative Requirements) .……………………………….…………..	9-4

1.	Bonding and Insurance.……………………………….…………………………………...	9-4

2.  	Procurement Standards.……………………………….…………………………………..	9-4

B.	STATE	.……………………………….………………………………………………….……….	9-5

1.  	Bid Security.……………………………….………………………………………………..	9-5

2.  	Contractor Licensing Fee (1% Tax on Gross Contractor Receipts) .………………….	9-5

3.  	Municipal Contracts and Franchises.……………………………….…………………….	9-5

4.  	County Contracts.……………………………….………………………………………….	9-6

5.  	Performance, Labor and Material Bonds.……………………………….……………….	9-6

6.  	Construction Contractor Registration is Required for All Bidders.…………………….	9-6

Montana Contractor Preference-- not applicable to CDBG Construction.………..	9-8

Grants for Projects Within Indian Reservations.……………………………….…… 9-8

III. 	RESPONSIBILITIES OF CDBG GRANT RECIPIENTS.……………………………….………	9-9

STEP 1 - SELECT ENGINEERING &/OR ARCHITECTURAL SERVICES.…………………	9-10

STEP 2 - PREPARE A BID PACKAGE.……………………………….…………………………	9-10

STEP 3 - OBTAIN BID DOCUMENT REVIEW AND APPROVAL.……………………………	9-13

STEP 4 - ADVERTISE A BID SOLICITATION.……………………………….…………………	9-13       	STEP 5 - LOG EACH BID RECEIVED.……………………………….…………………………	9-16

STEP 6 - CONDUCT THE BID OPENING.……………………………….……………………..	9-16

STEP 7 - REVIEW THE LOW BID.……………………………….………………………………	9-18

STEP 8 - OBTAIN DEBARMENT REVIEW OF THE LOW BIDDER.…………………………	9-18

STEP 9 - AWARD THE CONTRACT.……………………………….…………………………...	9-19

STEP 10 - HOLD A PRE-CONSTRUCTION CONFERENCE.………………………………..	9-20

STEP 11 - ISSUE NOTICE TO PROCEED.……………………………….…………………….	9-20

STEP 12 - MONITOR CONTRACTOR(S) ACTIVITIES.……………………………….………	9-21

Monitoring of the Contractor(s) by the Grant Recipient.……………………………	9-21

Contractor Retainage in the CDBG Program.……………………………….……...	9-22

STEP 13 - CONDUCT FINAL INSPECTION.……………………………….…………………..	9-23

STEP 14 - MAINTAIN RECORDS.……………………………….………………………………	9-24

IV. 	SPECIAL CONCERNS/REQUIREMENTS FOR PUBLIC FACILITIES PROJECTS.………	9-25

1.  	Water, Sewer, or Solid Waste Districts.……………………………….…………………	9-25

2.	Non-Profit Organizations or For-Profit Organizations as Subgrantees.………………	9-26

3.  	Paying System Assessments or Hook-up Costs for LMI Rental Families.……………	9-26

4.  	Construction of (or Modification to) Structures.……………………………….…………	9-27

5. 	Other Special Conditions and Circumstances.……………………………….………….	9-28

EXHIBITS.……………………………….………………………………………………….…………..	9-30

CHAPTER 10 -- HOUSING & COMMUNITY REVITALIZATION

A. 	Project Start-Up…….……………………………………………………………….………….……	10-2

B.  	Environmental Review…….………….…………………………………….………………….……	10-3

C.  	Procurement Standards………………….………………………………………...………….……	10-3

D.  Financial Management…….……………….………………………………………………….……	10-3

E.  	Civil Rights…….………………………….…………………………………………………….……	10-3

F.  	Labor Standards …….………………………………….……………………………….……….… 10-3

G.  Acquisition & Relocation………………….………………………………………...……………	..  10-4

H.  	Economic Development………………….………………………………………...……………….	10-6

I.   	Construction Management ………………….……………………………………….…….………	10-6

J.   	Housing………………….………………………………………...………….……………………..	10-6

K.  	Involving the Public………………….………………………………………...………….……	... 10-9

L.  	Project Monitoring………………….………………………………………...………….………….	10-9

M. 	Project Closeout………………….………………………………………...………….……………	10-9

N.  Project Audits………………….………………………………………...………….……	... 10-9

EXHIBITS………………….………………………………………...………….……………………….. 10-9

CHAPTER 11 – INVOLVING THE PUBLIC

I. 	OVERVIEW.……………………………….………………………………………………….…….	11-2

II.  	APPLICABLE REQUIREMENTS.……………………………….………………………………..	11-2

III.   	GRANTEE RESPONSIBILITIES.……………………………….………………………………..	11-3

A.	KEEPING THE PUBLIC INFORMED.……………………………….………………………..	11-3

B.	WORKING WITH THE MEDIA.……………………………….……………………………….	11-4

C.	PRESS RELEASES.……………………………….…………………………………………...	11-5

D.	PROJECT SIGNS.……………………………….……………………………………………..	11-6

E.	SPECIAL EVENTS.……………………………….…………………………………………….	11-7

F. 	OTHER PUBLIC INFORMATION TOOLS.……………………………….…………………..	11-8

G.	DEALING WITH COMPLAINTS.……………………………….……………………………...	11-8

EXHIBITS.……………………………….………………………………………………….…………….	11-10

### CHAPTER 12 -- PROJECT MONITORING

I.	OVERVIEW.……………………………….………………………………………………….……	12-2

II.    	PURPOSE OF PROJECT MONITORING.……………………………….……………………...	12-2

III.   	MONITORING PROCEDURES.……………………………….………………………………….	12-3

IV.  	ON-SITE PROJECT MONITORING.……………………………….…………………………….	12-4

V.   	MONITORING COMMENTS -- MONITORING LETTER / REPORT.………………………...	12-5

EXHIBITS.…………………………………………………….…………………………………………..	12-6

CHAPTER 13 -- PROJECT CLOSEOUT

I.	OVERVIEW.……………………………….………………………………………………….……	13-2

II.

GRANTEE PROJECT CLOSEOUT RESPONSIBILITIES.……………………………….……	13-2

1. 	PREPARE A PROJECT COMPLETION REPORT.……………………………….………...	13-2

2. 	DETERMINE FINAL AUDIT REQUIREMENTS.……………………………….…………….	13-3

3. 	COMPLETE CLOSEOUT FORMS AND CERTIFICATIONS.………………………………	13-3

A. 	Procedure if Organization-Wide Audits Are Required.……………………………….	13-3

B.  	Procedure if Separate Project Audits Are Required.……………………………….…	13-4

C.  	Program Income.……………………………….…………………………………………	13-5

D.  	Closeout Exhibits.……………………………….………………………………………..	13-6

EXHIBITS.……………………………….………………………………………………….…………….	13-7

CHAPTER 14 -- PROJECT AUDITS

I.	OVERVIEW.……………………………….………………………………………………….…….	14-2

II.    	APPLICABLE STATE AND FEDERAL LAWS.……………………………….…………………	14-2

A.	STATE	.……………………………….………………………………………………….……….	14-2

B.	FEDERAL.……………………………….………………………………………………….……	14-2

III.	AUDIT REQUIREMENTS.……………………………….………………………………………..	14-3

A. 	STATE AUDIT REQUIREMENTS.……………………………….……………………………	14-3

1.  	AUDIT REQUIREMENTS IN MONTANA LAW, SECT. 2-7-503(3) .………………..	14-3

2. 	THE PURPOSE OF THE MONTANA SINGLE AUDIT ACT.………………………..	14-4

3.	AUDIT AND AUDIT REPORT STANDARDS.……………………………….………...	14-4

B.	FEDERAL AUDIT REQUIREMENTS.……………………………….………………………..	14-4

GENERAL SCOPE OF AN OMB CIRCULAR A-133 AUDIT.………………………..	14-5

C.	SELECTION OF INDEPENDENT AUDITORS.……………………………….……………..	14-7

1.  	ROSTER OF INDEPENDENT AUDITORS.……………………………….…………..	14-7

2.  	CRITERIA FOR THE SELECTION OF THE INDEPENDENT AUDITOR.…………	14-9

3.	USE OF SMALL AND MINORITY AUDIT FIRMS.……………………………….…...	14-10

D.	AUDIT CONTRACTS.……………………………….………………………………………….	14-10

E.	AUDIT COSTS.……………………………….…………………………………………………	14-11

IV. 	AUDIT TRACKING.……………………………….………………………………………………..	14-11

V.   	SCOPE OF REQUIRED AUDITS.……………………………….……………………………….	14-11

VI.  	FILING OF AUDIT REPORTS.……………………………….…………………………………...	14-12

VII. 	ILLEGAL ACTS OR IRREGULARITIES.……………………………….………………………..	14-12

VIII.	RESOLUTION OF AUDIT FINDINGS.……………………………….…………………………..	14-12

X.   	AUDIT WORKPAPERS AND REPORTS.……………………………….………………………	14-13

EXHIBITS.……………………………….………………………………………………….…………….	14-14

CHAPTER 15 -- NEIGHBORHOOD STABILIZATION PROGRAM

### OVERVIEW.……………………………….………………………………………………….………….	15-2

A.    Chapter 1 Project Start-Up.……………………………….………………………………………	15-3

B.    Chapter 2 Environmental Review.……………………………….……………………………….	15-4

C.    Chapter 3 Procurement Standards.……………………………….……………………………..	15-4

D.    Chapter 4 Financial Management.……………………………….………………………………	15-4

E.    Chapter 5 Civil Rights.……………………………….…………………………………………….	15-5

F.    Chapter 6 Labor Standards.……………………………….………………………………………	15-6

G.   Chapter 7 Acquisition & Relocation.……………………………….……………………………..	15-6

H.    Chapter 8 Economic Development.……………………………….……………………………..	15-9

I.     Chapter 9 Construction Management.……………………………….…………………………..	15-9

J.    Chapter 10 Housing.……………………………….……………………………………………….	15-9

K.    Chapter 11 Involving the Public.……………………………….………………………………… 15-13

L.    Chapter 12 Project Monitoring.……………………………….…………………………………...	15-13

M.   Chapter 13 Project Closeout.……………………………….……………………………………..	15-13

N.    Chapter 14 Project Audits.……………………………….………………………………………..	15-13

EXHIBITS.……………………………….………………………………………………….…………….	15-14