## Sheet1
Exhibit 10-H
Sample Detailed CDBG Rehab Site Budget
Project Name: CDBG Rehab
Project Address:
Scope of work
New roof
minor siding repairs
trim trees
demo garage door and interior garage room
kitchen remodel
bathroom remodel
appliances
new furnace
new water heater
upgraded insulation in attic
new windows
install 2 egress windows in basement
demo basement kitchen
enlarge basement BR
[5 empty] | Revised | Actual | Under
Cost |  |  | Estimated | Change | Estimated | Cost to | (Over)
Code |  | Activity | Cost | Orders | Cost | Date | Budget
Example
|  | PROPERTY ACQUISITION | 84000
|  | CLOSING COSTS | 2000
|  | PRE-CONSTRUCTION | 86000
01 | 020 | Site clearing | 400
01 | 030 | Permits
01 | 041 | Demolition-Labor
01 | 045 | Demolition-Subcontractor
|  | demo kitchen | 320 | 1 MD
|  | demo bathroom | 320 | 1 MD
01 | 050 | Asbestos evaluation | 350
|  | LBP evaluation | 300
|  | Camera sewer line | 275
01 | 063 | Architect/Engineering fees
01 | 073 | Water hookup
01 | 083 | Sewer hookup
01 | 093 | Gas Service
01 | 103 | Temp power
01 | 113 | Portopotty
01 | 123 | Waste removal | 400
01 | 135 | House lifting/moving
01 | 140 | Equipment/tool rental
01 | 999 | Miscellaneous
|  | Subtotals | 2365
FOUNDATION
02 | 001 | Foundation- Labor
02 | 010 | Foundation-Materials
02 | 015 | Foundation-Subcontractor
02 | 020 | Excavation-Materials
02 | 022 | Excavation-Equipment
02 | 025 | Excavation-Subcontractor
02 | 035 | Utilities-Subcontractor
02 | 999 | Miscellaneous
Subtotals
FRAMING
03 | 001 | Framing- Labor
03 | 002 | Framing- Equipment
03 | 010 | Floors-Materials
03 | 015 | Framing-Subcontractor
03 | 020 | Framing Materials
03 | 040 | Fasteners-Materials
03 | 999 | Miscellaneous
Subtotals
EXTERIOR
04 | 001 | Exterior Finish- Labor
04 | 005 | Exterior Finish-Subcontractor | 4240
|  | Paint exterior house/garage (LBP) |  | 3600 | estimate
|  | Install and repair windows |  | 320 | 1 MD
|  | Install exterior doors |  | 320 | 1 MD
04 | 010 | Windows-Materials | 1000
04 | 020 | Exterior doors-Materials | 400
04 | 030 | Roofing-Materials
04 | 035 | Roofing-Subcontractor (House) | 2600 |  | estimate
04 | 040 | Exterior trim-Materials
04 | 050 | Soffit/facia-Materials
04 | 060 | Siding-Materials
04 | 070 | Replace Gutters | 400
| 080 | Steps/Deck-Materials
| 999 | Miscellaneous
|  | Subtotals | 8640
05 |  | INTERIOR FINISH
05 | 001 | Interior Finish- Labor
| 005 | Interior Finish-Subcontractor | 2240
|  | Install new kitchen/bath cabinets |  | 640 | 2 MD
|  | install interior doors |  | 320 | 1 MD
|  | frame mechanical room/door |  | 320 | 1 MD
|  | frame BR closet/bathroom |  | 320 | 1 MD
|  | frame laundry closet |  | 320 | 1 MD
|  | dry wall repairs/finish |  | 320 | 1 MD
05 | 015 | Electrical-Subcontractor | 1200
|  | install smoke alarm circuit |  | 1200
05 | 025 | HVAC-Subcontractor | 3600
|  | install new furnace/change ducts |  | 3600
| 035 | Plumbing-Subcontractor | 4800
pressure test plumbing and repair
install water heater
install kitchen sink
install bathroom fixtures
replumb laundry closet
repair handyman plumbing
05 |  | Insulation-Materials
05 | 040 | Insulation-Subcontractor | 1200
|  | blow in additional ceiling R-38 |  | 600
|  | insulate crawl space and rim joists |  | 600
05 | 045 | Drywall-Materials | 120
05 | 050 | Drywall-Subcontractor
05 | 055 | Tape/Texture-Materials
05 | 060 | Tape/Texture-Subcontractor
05 | 065 | Paint-Materials
05 | 070 | Paint-Subcontractor | 2400
05 | 075 | Flooring-Materials | 200
|  | kitchen sub flooring |  | 200
05 | 080 | Flooring-Subcontractor
05 | 085 | refinish 765 sqft hardwood floors | 2100
|  | vinyl 235 sqft kitchen, bathroom | 600
05 | 090 | Interior trim-Materials
|  | 7 interior doors | 420
05 | 100 | Bathroom Access-Materials | 200
05 | 110 | Cabinets/Counter tops-Materials | 2800
05 | 120 | Light fixtures-Materials | 300
05 | 130 | Appliances-Materials | 1500
05 | 140 | Miscellaneous (Chimney clean/insp)
| 999 | Subtotals | 23680
SITE WORK
06 |  | Site Work- Labor
|  | Site Work-Subcontractor | 1350
|  | replace 105 sqft sidewalk in back |  | 750
|  | remove side walk way |  | 300
|  | repair fence |  | 300
06 | 005 | Flatwork-Materials
06 | 010 | Flatwork-Subcontractor
06 | 015 | Sidewalks-Materials
06 | 020 | Landscaping-Materials
06 | 030 | Garage-Materials
06 | 040 | Miscellaneous
| 999 | Subtotals | 1350
SUPERVISION
07 |  | Supervision-Labor
| 001 | Subtotals
|  | TOTAL CONSTR/REHAB COSTS | 36035
|  | CONSTRUCTION CONTINGENCY | 5405.25