# EXHIBIT 9-M -- Construction Management Checklist

| Date(s) | 1. Set up a CDBG Public Facilities Construction (or Housing Construction) Management File. See Chapter 1, pages 1-17 and 1-20. Consult with your CDBG project liaison to clarify requirements. Review Section I (Construction Management) of the CDBG Project Monitoring Guide (Exhibit 12-A). |
| --- | --- |
|  | 2. Select engineering and/or architectural services in accordance with federal/state procurement standards appropriate for competitive negotiation. (Chapter 3, Procurement Standards and Chapter 9, page 9-10 and following) |
|  | 3. Prepare draft design plans and specifications and bid and contract document items -- including the required federal and state construction contract provisions. (Chapter 9, page 9-10and following; and Exhibit 9-J). |
|  | 4. (a) Use Exhibit 9-C to request all necessary reviews and approvals (of the plans and bid documents) from CDBG and from all other relevant funding agencies. (b) Secure CDBG approval of bid solicitation package:_____ |
|  | 5. Do the appropriate advertisement of bid solicitations. (Chapter 9, page 9-13 ff) |
|  | 6. Assure appropriate bid security procedures. (Chapter 9, page 9-16 and following) |
|  | 7. Conduct bid openings in a proper manner and give appropriate attention to bid review procedures. (Chapter 9, page 9-16 and following) |
|  | 8. Award construction contracts to the lowest responsible bidder within the required time -- after getting state and federal debarment/eligibility reviews from CDBG. (Chapter 9, page 9-18 and following) |
|  | 9. (a) Hold a pre-construction conference -- inform the prime contractor and all subcontractors performing contract construction work of their labor standards and civil rights obligations. Invite your CDBG liaison (Chapter 9, page 9-20 and following). (b) A complete copy of the signed contract and contract package should be sent to your CDBG liaison. |
|  | 10. Provide the required notices when initiating construction activities. (Chapter 9, page 9-208 and following). |
|  | 11. Monitor all contractors’ activities throughout the construction period -- to ensure that performance is in accord with the technical specifications and that compliance is maintained with all federal, state, and local standards and the terms of the contract(s). (Chapter 9, page 9-21 and following) |
|  | 12. Conduct the final inspection and file the required notices and reports with the appropriate agencies. (Chapter 9, page 9-23 and following) |
|  | 13. Throughout the project, assure compliance with labor standards (weekly payroll reviews, labor interviews, etc, as explained in Chapter 6), and secure CDBG and other agencies’ prior approval for change orders that affect the CDBG project budget, scope of work or construction schedule. |
|  | 14. Record and document Construction Management actions (Chapter 9, page 9-24 and following) in your Construction Management File (See Chapter 1, page 1-19). |